## Overview
Project Schedule
Overview
Start Date	01/22/21
Deadline	04/29/21
Today	02/22/21

Sprints
id	Start		End		Duration
	Planned	Actual	Planned	Actual	Planned	Actual
1	01/22/21	01/22/21	02/05/21	02/06/21	14	15
2	02/05/21	02/06/21	02/25/21		20
3	02/25/21		03/18/21		21
4
5
6

## Scrums
Planned Scrums
Overview
Project Start
Start	01/22/21
Number	14
id	Date	Sprint	Description
1	01/26/21	1
2	02/02/21	1
3	02/09/21	2	Discussed angular and direction of chess game
4	02/16/21	2	Discussed problems that occurred due to inclement weather and other courses. Discussed the chess system at large and problems with server.
5	02/23/21	2
6	03/02/21	3
7	03/09/21	3
8	03/16/21	3
9	03/23/21	4
10	03/30/21	4
11	04/06/21	5
12	04/13/21	5
13	04/20/21	6
14	04/27/21	6

## Backlog
Project Backlog
id	Task Name	Date	Completed	US	Sprint
01	Project Definition	01/21/21	YES	O66	1
02	Project Requirements	01/21/21	YES	O66	1
03	Project Specification	01/21/21		O66	2
04	Chess Subsystem	02/22/21		U1	2
05
06
07
08
09
10
11
12
13

## User Story
User Story
Description:

Code	Story
U1	User can play a game of chess
U2	User can play a game of chess online
U3	User can edit chess scenarios
U4	User can play chess scenarios
U5	User can learn information on chess moves
U6
U7
U8
U9
U10	User can play against computer

Special Codes
Code	Story
C22	Major background operation to carry the project.
O66
NCC-1701

418	Someone wrote code using the wrong method or tool and it needs to be resolved
Note: You can add some here, if it is appropriate

## Weekday Matrix
	Sunday	Monday	Tuesday`	Wednesday	Thursday	Friday	Saturday
Sunday	7	1	2	3	4	5	6
Monday	6	7	1	2	3	4	5
Tuesday	5	6	7	1	2	3	4
Wednesday	4	5	6	7	1	2	3
Thursday	3	4	5	6	7	1	2
Friday	2	3	4	5	6	7	1
Saturday	1	2	3	4	5	6	7